ITSU2006

IT PROJECT MANAGEMENT

ASSIGNMENT 2
GROUP PROJECT REPORT

AI-Powered Student Support Chatbot
Development and Implementation Plan

Prepared by: Samip Rana Magar
Group Leader: Smart Shrestha
Team Member: Ebnul
Project date: 25 October, 2026
Status: Completed

# Project Summary

This project proposes a plan for an AI-powered student support chatbot in a higher-education environment such as VIT. The chatbot would help students find approved information about course administration, important dates, learning support, student services and frequently asked questions. It should provide clear answers, point users to official sources, and refer uncertain or sensitive requests to an appropriate staff member. Institutional approval, data sources, integrations and implementation scope must be confirmed before development.

## Project Objectives

Define intended users, supported questions, boundaries and success criteria.

Design a conversational experience that makes approved student information easier to find.

Develop or prototype a chatbot using approved information sources and a controlled knowledge base.

Test answer quality, usability, accessibility, privacy and security before any pilot.

Document escalation, maintenance, monitoring and change-control processes.

## Scope and Boundaries

| In scope | Out of scope unless separately approved |
| --- | --- |
| Requirements gathering and student-support use cases | Making official academic decisions or changing student records |
| Prototype chatbot and curated FAQ/knowledge content | Unapproved connection to live LMS/SMS systems |
| Testing, evaluation, safety controls and handover plan | Treating chatbot output as authoritative legal, medical or visa advice |
| Privacy/security review and human escalation design | Using real student personal data without approval |

Planning assumption: the first release is a limited prototype using approved, non-sensitive information. Any connection to institutional systems or personal student data requires approval from the relevant system owners and privacy/security stakeholders.

# 1. Work Breakdown Structure (WBS)

The WBS decomposes the project into manageable work packages and deliverables, supporting planning, ownership and progress tracking [5], [6].

| WBS ID | Work package / activity | Deliverable |
| --- | --- | --- |
| 1.0 | Project initiation and governance | Approved project brief, objectives and roles |
| 1.1 | Confirm problem, users and stakeholders | Stakeholder register and user needs |
| 1.2 | Confirm scope, constraints and success measures | Scope statement and acceptance criteria |
| 2.0 | Requirements and knowledge planning | Requirements and content plan |
| 2.1 | Collect approved FAQs and official sources | Source inventory and content owners |
| 2.2 | Define intents, user journeys and escalation cases | Conversation flow and escalation rules |
| 2.3 | Define privacy, security and accessibility needs | Non-functional requirements checklist |
| 3.0 | Chatbot design and prototype | Working prototype or design demonstration |
| 3.1 | Select approved platform and architecture | Architecture and tool decision record |
| 3.2 | Design interface and conversation flow | Wireframes and conversation design |
| 3.3 | Build retrieval/knowledge workflow and response rules | Prototype chatbot |
| 4.0 | Testing and evaluation | Test results and issue log |
| 4.1 | Create test questions and expected answers | Evaluation dataset from approved sources |
| 4.2 | Test correctness, grounding and fallback behaviour | Evaluation results |
| 4.3 | Test privacy, security, usability and accessibility | Test checklist and defect register |
| 5.0 | Pilot and handover planning | Pilot recommendation and handover pack |
| 5.1 | Review results with stakeholders | Feedback and prioritised improvements |
| 5.2 | Prepare user guidance and maintenance plan | User guide, ownership and monitoring plan |
| 5.3 | Finalise report and presentation evidence | Final report and presentation |

## 1.1 Acceptance Criteria

Each in-scope requirement has an owner, status and test method.

Tested FAQ answers are supported by an approved source or clearly state that the answer cannot be verified.

The chatbot has a safe fallback and human escalation route for uncertain, sensitive or out-of-scope questions.

Test records include the question, expected result, actual result, pass/fail status and issue reference.

No live deployment or connection to student records occurs without explicit institutional approval.

# 2. Project Schedule and Milestones

The following is a relative two-week planning example, not an approved calendar commitment. Replace Day 1–Day 10 with confirmed dates and check team availability and assessment deadlines. Tasks may overlap only when prerequisites are available.

| ID | Activity | Start | Finish | Duration | Owner | Predecessor |
| --- | --- | --- | --- | --- | --- | --- |
| T1 | Confirm scope, stakeholders and success criteria | Day 1 | Day 1 | 1 day | Smart | — |
| T2 | Gather approved FAQs and define requirements | Day 1 | Day 3 | 3 days | Samip + Ebnul | T1 starts |
| T3 | Define architecture, conversation flow and safety boundaries | Day 2 | Day 4 | 3 days | Samip + technical lead* | T1 |
| T4 | Build/configure chatbot prototype | Day 4 | Day 7 | 4 days | Technical lead* + Ebnul | T2, T3 |
| T5 | Prepare test cases and evaluate answers | Day 6 | Day 8 | 3 days | Ebnul + Samip | T2; prototype available |
| T6 | Fix priority issues and complete privacy/security checks | Day 8 | Day 9 | 2 days | Technical lead* + Ebnul | T5 |
| T7 | Stakeholder review, handover plan and final report | Day 9 | Day 10 | 2 days | Smart + all members | T6 |

*Technical lead is a proposed role. Confirm whether a team member can perform it or limit the deliverable to a prototype/design.

## 2.1 Milestones

| Milestone | Target | Completion evidence |
| --- | --- | --- |
| Scope and success criteria agreed | Day 1 | Approved project brief |
| Requirements and approved content identified | Day 3 | Requirements list and source inventory |
| Prototype ready for evaluation | Day 7 | Prototype demonstration or screenshots |
| Testing and priority fixes complete | Day 9 | Test report and issue log |
| Report and presentation pack ready | Day 10 | Reviewed deliverables |

# 3. Gantt Chart and Dependencies

This simplified Gantt chart uses relative project days. Update it after actual dates are confirmed.

| Task | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| T1 Scope and stakeholders | ■ |  |  |  |  |  |  |  |  |  |
| T2 Requirements and content | ■ | ■ | ■ |  |  |  |  |  |  |  |
| T3 Architecture and conversation design |  | ■ | ■ | ■ |  |  |  |  |  |  |
| T4 Build/configure prototype |  |  |  | ■ | ■ | ■ | ■ |  |  |  |
| T5 Evaluation and test cases |  |  |  |  |  | ■ | ■ | ■ |  |  |
| T6 Fixes and security/privacy checks |  |  |  |  |  |  |  | ■ | ■ |  |
| T7 Review and handover |  |  |  |  |  |  |  | ■ | ■ |  |

## 3.1 Dependency Logic

T1 → T2: requirements gathering depends on agreed scope and stakeholder needs.

T1 → T3: design depends on agreed use cases and boundaries.

T2 + T3 → T4: prototype work needs approved content and a defined design.

T4 → T5: end-to-end evaluation requires a testable prototype; test-case preparation may begin earlier.

T5 → T6: fixes and final checks are prioritised using recorded test findings.

T6 → T7: handover recommendations should reflect resolved critical issues and known limitations.

## 3.2 Schedule Monitoring

Update task status at least twice per week and review progress against milestones. Log delays with their cause, impact on dependent tasks, owner and recovery action. Changes to scope or dates should be agreed by the group leader and recorded in the repository [5], [6].

# 4. Resource Allocation Plan

Allocations are provisional and should be adjusted to reflect actual skills, workload and access to approved tools.

| Resource / role | Responsibilities | Planned involvement |
| --- | --- | --- |
| Smart Shrestha — Group Leader | Coordinate project; confirm scope/stakeholders; approve group decisions; integrate report and submission | Across project; milestone reviews |
| Samip Rana Magar — Planning and Scheduling | Maintain WBS, schedule, Gantt, resource plan, RACI and communication plan | Across project; update planning artefacts |
| Ebnul — Risk, Quality and Configuration | Maintain risk/issue log, testing approach, change requests, quality checks and repository records | Across project; focus on testing/review |
| Technical lead / developer* | Configure or develop prototype, document architecture and resolve technical defects | Design, build and testing |
| Student/stakeholder reviewers* | Review use cases, clarity, usefulness and escalation experience | Requirements and prototype review |

## 4.1 Tools and Supporting Resources

| Tool / resource | Purpose | Control / note |
| --- | --- | --- |
| GitHub | Version control for report, code and artefacts | Restrict access; never commit credentials or personal data [7] |
| Jira or equivalent | Assign tasks, track status, issues and changes | Use consistent statuses, owners and due dates |
| Approved chatbot platform/framework | Build or demonstrate chatbot | Check institutional approval and data handling |
| Approved FAQs and official student information | Provide grounded answers | Record source owner, date and review status |
| Test question set | Evaluate answer quality and fallback | Use synthetic or non-sensitive inputs |

## 4.2 Resource Management

Smart coordinates workload conflicts and decisions. Samip checks owners, durations and dependencies. Ebnul tracks risks, quality evidence, issues and changes. The technical lead provides technical estimates only if the role is confirmed. If time is insufficient for full implementation, reduce scope transparently to a proof of concept rather than overstating the result.

# 5. Responsibility Matrix (RACI)

R = Responsible; A = Accountable; C = Consulted; I = Informed. Each activity should have one clearly identified accountable role [5].

| Activity | Smart / Leader | Samip / Planning | Ebnul / Risk & Quality | Technical lead* | Stakeholder* |
| --- | --- | --- | --- | --- | --- |
| Project initiation and scope | A/R | C | C | I | C |
| Requirements and source inventory | A | R | R | C | C |
| WBS, schedule and Gantt chart | C | A/R | C | C | I |
| Chatbot design and prototype | C | C | C | A/R* | I |
| Risk and issue register | C | C | A/R | C | I |
| Testing and quality checks | C | R | A/R | R* | C |
| Change requests and version control | A | C | R | C | I |
| Final report and presentation | A | R | R | C | I |

*Proposed roles; confirm assignments. If technical lead is not a separate member, assign duties to a named member and update the matrix.

## 5.1 Governance

Smart coordinates major decisions and final integration. Samip maintains planning artefacts and reports schedule risks. Ebnul maintains risk, issue, quality and change records. Decisions affecting scope, data access, deployment or real student information must be documented and escalated for appropriate institutional approval.

# 6. Risk and Issue Management

AI chatbots may produce unsupported answers, expose sensitive information, be manipulated by prompt injection, or cause users to over-rely on automated responses. A risk-based approach should identify, assess, treat and monitor risks throughout the project [1]–[4].

| ID | Risk | Initial priority | Mitigation / response | Owner |
| --- | --- | --- | --- | --- |
| R1 | Incorrect or unsupported chatbot answers | High | Use approved sources; prefer grounded answers; provide uncertainty language and human escalation; test representative questions | Ebnul |
| R2 | Personal/confidential information exposed | High | Use synthetic test data; minimise collection; restrict access; review retention and privacy terms; no live student data without approval | Ebnul + Smart |
| R3 | Prompt injection or malicious input | High | Constrain behaviour; test adversarial prompts; limit tool permissions; separate trusted instructions from user content | Technical lead* + Ebnul |
| R4 | Platform or integration unavailable | Medium | Confirm access early; prepare standalone prototype fallback; document assumptions | Samip + technical lead* |
| R5 | Schedule too short for full implementation | High | Prioritise minimum viable prototype; define exclusions; track dependencies; escalate delays early | Smart + Samip |
| R6 | Students treat responses as official decisions | Medium | State limitations; link official sources; refer sensitive cases to staff | Smart + Ebnul |

Risk ratings are preliminary qualitative estimates and should be reviewed by the team. This register does not replace formal institutional privacy, security or AI governance review.

## 6.1 Issue Management

Record each issue with ID, description, date raised, severity, owner, target resolution and status.

Prioritise issues that could expose data, mislead students or block a required deliverable.

Escalate critical privacy/security concerns; do not proceed with risky data access or deployment while approval is unresolved.

Retest fixes and record evidence before closing an issue.

# 7. Change Request Management

A change request records a proposed change to scope, requirements, schedule, platform, content or deliverables. Change control prevents informal requests from undermining the plan [5], [6].

| Step | Procedure |
| --- | --- |
| 1. Submit | Requester records the proposed change, reason and expected benefit in the issue tracker. |
| 2. Assess | Samip assesses schedule/scope impact; Ebnul assesses risk/quality impact; technical lead assesses feasibility if appointed. |
| 3. Decide | Smart coordinates and records an approve, reject or defer decision with the group and relevant stakeholder. |
| 4. Update | If approved, update scope, schedule, WBS, RACI, risk log and version-controlled artefacts as needed. |
| 5. Verify | Check acceptance criteria and record the outcome. |

# 8. Communication Management Plan

The communication plan defines what information is shared, with whom, how often and by whom.

| Communication | Audience | Frequency | Method | Owner | Output |
| --- | --- | --- | --- | --- | --- |
| Team progress meeting | Smart, Samip, Ebnul | Weekly or as agreed | Online/in person | Smart | Decisions, actions and blockers |
| Task status updates | All team members | At least twice weekly | Jira or equivalent | Each task owner | Updated status and due dates |
| Planning/dependency review | Smart, Samip, Ebnul | At milestones or when delayed | Shared schedule | Samip | Updated schedule and recovery actions |
| Risk and quality review | Team and technical lead if appointed | During build/testing | Risk and issue register | Ebnul | Risk ratings and test issues |
| Stakeholder review | Group and nominated reviewers | Requirements/prototype milestones | Demo or written review | Smart | Feedback and decisions |
| Security/privacy escalation | Authorised decision-makers | Immediately for critical issues | Approved secure channel | Issue owner | Escalation record and decision |

## 8.1 Communication and Record-Keeping Rules

Record decisions that affect scope, deadlines, quality or data access.

Share security/privacy findings only with authorised recipients.

Use the approved repository for versioned artefacts; do not store secrets or personal student data.

Every major task should have an owner, current status and next action.

# 9. Quality Management and Testing

Quality management checks whether the chatbot meets agreed requirements and communicates its limitations. AI risk guidance supports ongoing testing, evaluation, monitoring and clear accountability [1], [2].

| Quality dimension | Acceptance expectation | Evidence |
| --- | --- | --- |
| Correctness and grounding | Answers match approved sources; unsupported answers trigger fallback/referral | Test set with expected answers and source links |
| Coverage | Representative in-scope questions are handled; unsupported requests identified | Use-case coverage checklist |
| Safety and privacy | No real personal data in tests; sensitive requests escalated; data handling reviewed | Privacy/security checklist and test log |
| Robustness | Ambiguous, misspelled and adversarial requests do not bypass controls | Boundary/adversarial test cases |
| Usability/accessibility | Students understand responses, limitations and escalation options | User review and feedback summary |
| Maintainability | Content has an owner and review date; changes are traceable | Repository history and content register |

## 9.1 Test Process

Prepare test questions covering common FAQs, ambiguous queries, out-of-scope requests and sensitive scenarios.

Define expected answer, trusted source, pass criteria and severity before testing.

Record actual responses and classify failures as incorrect, unsupported, incomplete, unsafe or unclear.

Fix high-priority defects and rerun relevant tests; report unresolved limitations in the final submission.

Do not claim production readiness based only on a small demonstration dataset.

# 10. Configuration Management Using GitHub

GitHub or an approved equivalent can track project artefacts, changes and collaboration history [7]. The team should agree on repository structure and naming conventions before contributing.

Keep the report, requirements, diagrams, test plan, issue references and approved documents in version control.

Use clear commit messages and review changes before merging into the main branch.

Restrict repository access to authorised team members.

Never commit passwords, API keys, access tokens, private student records or confidential data.

Maintain a change log linking important artefact changes to approved requests.

| Suggested folder | Contents |
| --- | --- |
| /docs | Report drafts, meeting notes and decisions |
| /requirements | Scope, user stories, acceptance criteria and source inventory |
| /design | Conversation flows, architecture and interface sketches |
| /tests | Test cases, results and issue summaries using non-sensitive data |
| /project-management | WBS, schedule, RACI, risk register and change log |

# 11. Success Measures and Deliverables

| Measure | Target / evidence |
| --- | --- |
| Planning completeness | Required project-management sections have owners, deliverables and review status |
| Prototype functionality | Demonstrates agreed high-priority student-support use cases |
| Answer quality | Evaluation results documented against a predefined test set; failures reported transparently |
| Safety and privacy | Escalation tested; no unapproved live data or integrations used |
| Traceability | Requirements, test cases, issues and changes link to versioned artefacts |
| Team collaboration | Task board, repository history, meeting notes and contribution evidence retained if required |

# 12. Conclusion

This plan provides a structured approach to an AI-powered student support chatbot, from requirements and prototype design through evaluation, risk treatment and handover. The project should remain a prototype or controlled proof of concept unless the institution approves deployment, platform use and any integration with student systems. The group should confirm dates, technical responsibilities, assessment requirements and stakeholder access before finalising the report.

# References

[1] National Institute of Standards and Technology, Artificial Intelligence Risk Management Framework (AI RMF 1.0), NIST AI 100-1, Jan. 2023. [Online]. Available: https://doi.org/10.6028/NIST.AI.100-1.

[2] National Institute of Standards and Technology, Artificial Intelligence Risk Management Framework: Generative Artificial Intelligence Profile, NIST AI 600-1, Jul. 2024. [Online]. Available: https://doi.org/10.6028/NIST.AI.600-1.

[3] OWASP Foundation, “OWASP Top 10 for Large Language Model Applications,” 2025. [Online]. Available: https://genai.owasp.org/llm-top-10/.

[4] Office of the Australian Information Commissioner, “Australian Privacy Principles.” [Online]. Available: https://www.oaic.gov.au/privacy/australian-privacy-principles. [Accessed: Oct. 25, 2026].

[5] Project Management Institute, A Guide to the Project Management Body of Knowledge (PMBOK® Guide), 7th ed., and The Standard for Project Management. Newtown Square, PA, USA: Project Management Institute, 2021.

[6] Project Management Institute, Process Groups: A Practice Guide. Newtown Square, PA, USA: Project Management Institute, 2022.

[7] GitHub, “About repositories,” GitHub Docs. [Online]. Available: https://docs.github.com/en/repositories/creating-and-managing-repositories/about-repositories. [Accessed: Oct. 25, 2026].